## Daily Tasks
Day | Date | Task Completed | Remarks
Wed | 2022-05-18 | Gathered requirements from web & meet
Thu | 2022-05-19 | Created Basic Architecture of Node.js Express App from scratch
Fri | 2022-05-20 | User & Session models & implemented Auth middleware
Sat | 2022-05-21 | Implemented Sessions via tokens from DB
Sun | 2022-05-22 | OFF DAY
Mon | 2022-05-23 | Implemented User CRUD APIs
Tue | 2022-05-24 | Register, Login, forgot, reset & new-password APIs
Wed | 2022-05-25 | Implemented NodeMailer package for resetting link via email | Implemented customized functions for reusability
Thu | 2022-05-26 | Implemented UserAddresses CRUD APIs
Fri | 2022-05-27 | Upload UserImage & delete image with file implemented
Sat | 2022-05-28 | Implemented Seller model with APIs
Sun | 2022-05-29 | OFF DAY |  | 1 | Set Endpoints API like | /api/users | Get All users
Mon | 2022-05-30 | Category APIs & Brand API implemented |  |  |  | /api/users/:id | Get a user
Tue | 2022-05-31 | Gathered requirements from website about Product API, images array etc
Wed | 2022-06-01 | Set all Endpoints in a standard way like api & resource naming convention /api/users |  | 2 | Updated method {new: true}
Thu | 2022-06-02 |  |  |  | .findByIdAndUpdate({condition}, {DataForUpdate}, {Options})
Fri | 2022-06-03 |  |  |  | it will return the updated object
Sat | 2022-06-04
Sun | 2022-06-05 | OFF DAY
Mon | 2022-06-06 | Implement sharp library for making thumbnails of images where necessary |  |  | working on getAddresses Endpoint
Tue | 2022-06-07
Wed | 2022-06-08
Thu | 2022-06-09
Fri | 2022-06-10
Sat | 2022-06-11
Sun | 2022-06-12 | OFF DAY

## Sheet1
Product
online_only
ratings (Number)
Review
product_id | FK
user_id | FK
Issues to be discussed:
Email Preferences
Product Reviews
sellers ??
Project hosting
|  |  | Categories | Products | Reviews
products_addon |  |  | category (shaheryar) | product_name | product_id
|  |  |  | category_ids | user_id
delivery charges depends on zip code |  |  |  |  | comments
|  |  |  | online_only (Yes/No) | attachment | Array of images
[5 empty] | rating | 1 - 5
Sellers | DashBoard | Products CRUD, Relevant Orders etc |  |  | status | pending, approved, rejected
Admin | DashBoard | Product, Orders, CMS
User
Store / Franchise |  |  |  |  | Stock Management
title | string |  |  |  | product_id
banner | string | image |  |  | variant
email | string
phone_no | string |  |  |  | sku
address | string |  |  |  | price
city | string |  |  |  | qty
state | string
country | string
zip | string
is_deleted | boolean

## Sheet2
DB Collections | Products
Carts
Orders
Reviews
product_id
user_id
comments
attachment
rating
status

## Meeting Points
category with sub categories | api not working
Filters options to be added in Category Model
Filter endpoints
discounted products | to be discussed
Feedback
Reviews based ratings

## Sheet3
Store users FORM doesn't contain Store ID
cart post route is based on user ID params
product needs to be add new with update controller & api endpoints
Image lib of Next.js implemented
actualPrice & SalePrice is necessary for calculating profit
product colors need to be display via Dashboard (from Images)
Payment Methods ?? | authorized.net | sema credit | paypal
Order
Order Tracking
Reviews & Rating
Wishlist ??
Discount ??? | coupon based | product based %
CHATBOT
Payment Gateway
slider url implement in Dashboard
categories with nested levels